## Deliverables_A-D
Package | Item

## Stages
Stage | Status | Details

## Artifacts
Name | Stage | Status | Notes

## Acceptance_Criteria
Criterion
Jet coherence ≥ 0.90
Ripple amplitude −30–50% vs straight inlet; no entrainment increase
ELC drift ≤ 0.1 Hz; no hunting
Power between 10 and 12 kW

## Sections
Section | Title

## Tests
Test_ID | Name | Objective | Setup | Parameters | Instruments | Acceptance_Criteria | Status | Stage | Linked_Artifacts
T-001 | Jet_Coherence_Test | Assess jet coherence; ensure coherent jet meets threshold. | Bench Test Pack; imaging config |  | Imaging setup (per imaging config). | Jet coherence ≥ 0.90 | Defined | B | Procedure; Datasheet; Imaging config
T-002 | Tank_Ripple_Test | Measure tank ripple amplitude reduction vs straight inlet; verify no entrainment increase. | Bench Test Pack; PT mounting sketch |  | Pressure transducer (PT). | Ripple amplitude −30–50% vs straight inlet; no entrainment increase | Defined | B | Procedure; Datasheet; PT mounting sketch
T-003 | Electrical_Stability | Verify ELC drift ≤ 0.1 Hz with no hunting | Generator + ELC narrow window; nominal load |  | ELC + scope/logger | ELC drift ≤ 0.1 Hz; no hunting | Defined | C | Procedure; Logger config
T-004 | Power_Output | Confirm net electrical power within 10–12 kW at operating head | Turbine+generator; calibrated meters |  | Wattmeter + V/I sensors | Power between 10 and 12 kW | Defined | C | Procedure; Datasheet

## Measurements
Timestamp | Test_ID | Sensor | Value | Unit | Baseline_Value | Conditions | Notes | Pass | Rule_Eval
2026-01-21T11:42:32 | T-001 | coherence | 0.9399 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T11:44:32 | T-001 | coherence | 0.9145 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T11:46:32 | T-001 | coherence | 0.9459 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T11:48:32 | T-001 | coherence | 0.9809 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T11:50:32 | T-001 | coherence | 0.9106 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T11:52:32 | T-001 | coherence | 0.9106 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T11:54:32 | T-001 | coherence | 0.9832 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T11:56:32 | T-001 | coherence | 0.9507 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T11:58:32 | T-001 | coherence | 0.9012 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:00:32 | T-001 | coherence | 0.9417 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:02:32 | T-001 | coherence | 0.9015 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:04:32 | T-001 | coherence | 0.9014 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:06:32 | T-001 | coherence | 0.9297 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:08:32 | T-001 | coherence | 0.8435 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:10:32 | T-001 | coherence | 0.851 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:12:32 | T-001 | coherence | 0.8975 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:14:32 | T-001 | coherence | 0.8795 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:16:32 | T-001 | coherence | 0.9326 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:18:32 | T-001 | coherence | 0.8837 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:20:32 | T-001 | coherence | 0.8635 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:22:32 | T-001 | coherence | 0.9786 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:24:32 | T-001 | coherence | 0.911 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:26:32 | T-001 | coherence | 0.9227 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:28:32 | T-001 | coherence | 0.863 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:30:32 | T-001 | coherence | 0.8982 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:32:32 | T-001 | coherence | 0.9244 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:34:32 | T-001 | coherence | 0.874 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:36:32 | T-001 | coherence | 0.935 |  |  | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T11:42:32 | T-002 | ripple | 9.2977 | mm | 11.3994 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T11:45:32 | T-002 | ripple | 6.7182 | mm | 11.7083 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T11:48:32 | T-002 | ripple | 7.4373 | mm | 12.8225 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T11:51:32 | T-002 | ripple | 5.3488 | mm | 10.7792 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T11:54:32 | T-002 | ripple | 6.3564 | mm | 12.7385 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T11:57:32 | T-002 | ripple | 6.467 | mm | 12.1714 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:00:32 | T-002 | ripple | 8.3711 | mm | 10.5215 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:03:32 | T-002 | ripple | 6.6065 | mm | 11.2802 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:06:32 | T-002 | ripple | 8.5865 | mm | 12.3241 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:09:32 | T-002 | ripple | 8.8005 | mm | 11.6149 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:12:32 | T-002 | ripple | 9.4836 | mm | 13.031 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:15:32 | T-002 | ripple | 6.1937 | mm | 12.9313 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:18:32 | T-002 | ripple | 5.745 | mm | 12.3313 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:21:32 | T-002 | ripple | 6.8939 | mm | 12.9755 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:24:32 | T-002 | ripple | 10.549 | mm | 12.8125 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:27:32 | T-002 | ripple | 8.3919 | mm | 13.3562 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:30:32 | T-002 | ripple | 10.2416 | mm | 12.3614 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:33:32 | T-002 | ripple | 7.5391 | mm | 13.538 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:36:32 | T-002 | ripple | 6.976 | mm | 12.087 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:39:32 | T-002 | ripple | 9.0078 | mm | 11.701 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:42:32 | T-002 | ripple | 6.3244 | mm | 13.4779 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:45:32 | T-002 | ripple | 5.6296 | mm | 11.4817 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:48:32 | T-002 | ripple | 9.7482 | mm | 12.9154 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:51:32 | T-002 | ripple | 10.3493 | mm | 12.3288 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:54:32 | T-002 | ripple | 6.2904 | mm | 11.2979 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T12:57:32 | T-002 | ripple | 10.6986 | mm | 11.6723 | Head=7.5m; Flow=45 L/s | synthetic
2026-01-21T11:42:32 | T-003 | elc drift | 0.0658 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T11:46:32 | T-003 | elc drift | 0.0455 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T11:50:32 | T-003 | elc drift | 0.0536 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T11:54:32 | T-003 | elc drift | 0.1326 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T11:58:32 | T-003 | elc drift | 0.0792 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T12:02:32 | T-003 | elc drift | 0.098 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T12:06:32 | T-003 | elc drift | 0.1276 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T12:10:32 | T-003 | elc drift | 0.0511 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T12:14:32 | T-003 | elc drift | 0.0326 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T12:18:32 | T-003 | elc drift | 0.0652 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T12:22:32 | T-003 | elc drift | 0.0495 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T12:26:32 | T-003 | elc drift | 0.1268 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T12:30:32 | T-003 | elc drift | 0.0643 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T12:34:32 | T-003 | elc drift | 0.1269 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T12:38:32 | T-003 | elc drift | 0.1633 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T12:42:32 | T-003 | elc drift | 0.081 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T12:46:32 | T-003 | elc drift | 0.0743 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T12:50:32 | T-003 | elc drift | 0.0675 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T12:54:32 | T-003 | elc drift | 0.0885 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T12:58:32 | T-003 | elc drift | 0.0431 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T13:02:32 | T-003 | elc drift | 0.0714 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T13:06:32 | T-003 | elc drift | 0.1112 | Hz |  | Nominal load 8 kW | synthetic
2026-01-21T11:42:32 | T-004 | power | 10.5077 | kW |  | Head=7.5m | synthetic
2026-01-21T11:47:32 | T-004 | power | 10.4139 | kW |  | Head=7.5m | synthetic
2026-01-21T11:52:32 | T-004 | power | 10.7961 | kW |  | Head=7.5m | synthetic
2026-01-21T11:57:32 | T-004 | power | 9.1238 | kW |  | Head=7.5m | synthetic
2026-01-21T12:02:32 | T-004 | power | 11.0746 | kW |  | Head=7.5m | synthetic
2026-01-21T12:07:32 | T-004 | power | 10.5114 | kW |  | Head=7.5m | synthetic
2026-01-21T12:12:32 | T-004 | power | 11.8679 | kW |  | Head=7.5m | synthetic
2026-01-21T12:17:32 | T-004 | power | 10.5695 | kW |  | Head=7.5m | synthetic
2026-01-21T12:22:32 | T-004 | power | 12.6025 | kW |  | Head=7.5m | synthetic
2026-01-21T12:27:32 | T-004 | power | 10.7103 | kW |  | Head=7.5m | synthetic
2026-01-21T12:32:32 | T-004 | power | 11.4067 | kW |  | Head=7.5m | synthetic
2026-01-21T12:37:32 | T-004 | power | 12.8019 | kW |  | Head=7.5m | synthetic
2026-01-21T12:42:32 | T-004 | power | 12.8068 | kW |  | Head=7.5m | synthetic
2026-01-21T12:47:32 | T-004 | power | 10.1166 | kW |  | Head=7.5m | synthetic
2026-01-21T12:52:32 | T-004 | power | 11.2943 | kW |  | Head=7.5m | synthetic
2026-01-21T12:57:32 | T-004 | power | 10.3895 | kW |  | Head=7.5m | synthetic
2026-01-21T13:02:32 | T-004 | power | 11.3454 | kW |  | Head=7.5m | synthetic
2026-01-21T13:07:32 | T-004 | power | 10.5037 | kW |  | Head=7.5m | synthetic
2026-01-21T13:12:32 | T-004 | power | 12.3929 | kW |  | Head=7.5m | synthetic
2026-01-21T13:17:32 | T-004 | power | 11.4395 | kW |  | Head=7.5m | synthetic
2026-01-21T13:22:32 | T-004 | power | 9.2773 | kW |  | Head=7.5m | synthetic
2026-01-21T13:27:32 | T-004 | power | 10.5774 | kW |  | Head=7.5m | synthetic
2026-01-21T13:32:32 | T-004 | power | 11.8514 | kW |  | Head=7.5m | synthetic
2026-01-21T13:37:32 | T-004 | power | 11.7057 | kW |  | Head=7.5m | synthetic

## Dashboard
MicroHydroV1 — Test Summary (Synthetic)
Summary by Test_ID
Test_ID | Total | Pass | Fail
T-001
T-002
T-003
T-004
TOTAL

## Trends
T-001 — Coherence vs Time
Timestamp | Value
T-002 — Ripple vs Time (with 70% Threshold)
Timestamp | Value | Baseline | Threshold_70%
T-003 — ELC Drift vs Time
Timestamp | Value (Hz)
T-004 — Power Output vs Time (10–12 kW band)
Timestamp | Power (kW) | Lower | Upper