## Sheet1
Workstream | Owner | Start | End | Tasks | Entry | Exit
CAD & QA | Nathan | 2026-01-22 | 2026-01-23 | Freeze params.json; Run MHV1_GenerateAll → RunQA → ExportAll → GenDrawings; check QA PASS | Params agreed | QA ALL PASS; STEP/STL & drawings exported
Bench – Stage B | Nathan | 2026-01-23 | 2026-01-26 | Run ΔP–Q matrix across heads 2–8 m for vane angles 10/20/30°; T‑001 coherence; T‑002 ripple | Bench calibrated; templates verified | Monotonic ΔP–Q; T‑001 ≥0.90; T‑002 −30–50%
Electrical – Stage C | Nathan | 2026-01-26 | 2026-01-28 | T‑003 frequency drift under nominal load; T‑004 power window 10–12 kW across targets | Stable hydraulic operating points | Drift ≤0.1 Hz; 10–12 kW band confirmed
Docs & STW | Nathan | 2026-01-28 | 2026-01-29 | Fill STW vNext Matrix; finalize Go/No‑Go Packet; update stakeholder deck | B/C evidence in dashboards | Packet signed; Admit/Hold locked